## WBS
Work Breakdown Structure
Phases | Activity ID | Activity Description | Predecessor ID | Effort (Days)
1 | Project Initiation
| 1.1 | Project Objectives | 0 | 1
| 1.2 | Identify the stakeholders (students, lecturers, registration staff, student services staff) | 1.1 | 1
| 1.3 | Specifications and requirements of the project | 1.2 | 1
| 1.4 | Define and assign project roles and responsibilities | 1.3 | 2
2 | Planning Phase
| 2.1 | Problem Definition | 1.4 | 2
| 2.1.1 | Study the current course registration system | 2.1 | 1
| 2.1.2 | Identify problems with the current system | 2.1.1 | 1
| 2.1.3 | Define system scope and limitations | 2.1.2 | 1
2.2 System Vision Development
| 2.2.1 | Develop system vision document | 2.1.3 | 2
| 2.2.2 | Define major system features | 2.2.1 | 1
| 2.2.3 | Identify system users | 2.2.2 | 1
2.3 Context Diagram Development
| 2.3.1 | Identify the external entities | 2.2.3 | 2
| 2.3.2 | Identify system inputs and outputs | 2.3.1 | 2
| 2.3.3 | Draw a contextual diagram (identify the right type of diagram to draw) | 2.3.2 | 3
2.4 Project Scheduling
| 2.4.1 | Develop a Work Breakdown Structure | 2.3.3 | 2
| 2.4.2 | Identity project tasks | 2.4.1 | 1
| 2.4.3 | Estimate task duration | 2.4.2 | 1
| 2.4.4 | Develop Gantt chart | 2.4.3 | 1
3 | Analysis Phase
3.1 System Requirements Gathering
| 3.1.1 | Identify interviewees | 2.4.4 | 1
| 3.1.2 | Prepare interview questions | 3.1.1 | 2
| 3.1.3 | Conduct interviews | 3.1.2 | 1
| 3.1.4 | Document requirements | 3.1.3 | 1
| 3.2 Functional Requirements Analysis | Functional Requirements Analysis
| 3.2.1 | Analyze enrolment subsystem requirements | 3.1.4 | 3
| 3.2.2 | Analyze admission subsystem requirements | 3.2.1 | 3
| 3.2.3 | Analyze dormitory allocation subsystem requirements | 3.2.2 | 3
| 3.3 | Data Flow Modelling |  | 3
| 3.3.1 | Develop Level-0 Data Flow Diagram | 3.2.3 | 3
| 3.3.2 | Develop Level-1 Data Flow Diagrams | 3.3.1 | 3
3.4 Use Case Modelling
| 3.4.1 | Identify actors | 3.3.2 | 1
| 3.4.2 | Identify system use cases | 3.4.1 | 2
| 3.4.3 | Develop Use Case Diagram | 3.4.2 | 3
| 3.5 | Data Modelling |  | 1
| 3.5.1 | Identify system entities | 3.4.3 | 1
| 3.5.2 | Identify relationships | 3.5.1 | 1
| 3.5.3 | Develop an Entity-Relationship diagram | 3.5.2 | 3
4 | Design Phase
4.1 Define system architecture
| 4.1.1 | Define system architecture | 3.5.3 | 2
| 4.1.2 | Define subsystem interactions | 4.1.1 | 3
| 4.1.3 | Design shared database structure | 4.1.2 | 2
| 4.2 | Database Design | 4.1.3 | 3
| 4.2.1 | Design student database tables | 4.2 | 2
| 4.2.2 | Design staff database tables | 4.2.1 | 2
| 4.2.3 | Designing enumeration records | 4.2.2 | 3
| 4.2.4 | Design dormitory allocation tables | 4.2.3 | 2
| 4.3 User Interface Design | User Interface Design | 4.2.4 | 2
| 4.3.1 | Input Design | 4.3 | 2
| 4.3.1.1 | Student registration form | 4.3.1 | 2
| 4.3.1.2 | Unit enrolment form | 4.3.1.1 | 2
| 4.3.1.3 | Student information update form | 4.3.1.2 | 2
| 4.3.1.4 | Dormitory allocation form | 4.3.1.3 | 2
| 4.3.2 | Output Design | 4.3.1.4 | 2
| 4.3.2.1 | Student profile display | 4.3.2 | 2
| 4.3.2.2 | Student transcript report | 4.3.2.1 | 2
| 4.3.2.3 | Unit enrolment list | 4.3.2.2 | 2
| 4.3.2.4 | Dormitory allocation report | 4.3.2.3 | 2
| 4.4 | System Interface Design | 4.3.2.4 | 2
| 4.4.1 | Define communication with the billing system | 4.4 | 4
| 4.4.2 | Define subsystem integration | 4.4.1 | 4
4.5 Network Design
| 4.5.1 | Design campus network architecture | 4.4.2 | 4
| 4.5.2 | Develop IP address scheme | 4.5.1 | 2
5 | Documentation and Appendices
5.1 Assumptions
| 5.1.1 | Identify system assumptions | 4.5.2 | 2
5.2 Glossary
| 5.2.1 | Define technical terms used in the report | 5.1.1 | 1